## Original plan
Week | Goal | Estimated difficulty ( 0-10)
08.01.2024 | Understand the starter files | 6
15.01.2024 | Make a github repo | 3
22.01.2024 | add makefile | 4
29.01.2024 | integrate github actions | 6
05.02.2024 | run test | 6
12.02.2024 | cloning the repo to azure | 3
19.02.2024 | run tests | 6
26.02.2024 | build azure pipeline | 7
04.03.2024 | test | 7
13.03.2024 | test | 7
18.03.2024 | video recording for the demo | 4
25.03.2024 | submission | 1

## Actual plan
Week | Goal | Estimated difficulty ( 0-10)
08.01.2024 | Understand the starter files | 7
15.01.2024 | Make a github repo | 3
22.01.2024 | add makefile | 5
29.01.2024 | integrate github actions | 6
05.02.2024 | run test + cloning the repo to azure | 6
12.02.2024 | run tests + build azure pipeline | 8
19.02.2024 | test | 6
26.02.2024 | video recording for the demo | 3
04.03.2024 | submission | 1
13.03.2024
18.03.2024
25.03.2024